## Sheet1
Project Log
S/N | Task | Date | Matthew (hrs) | Fyonn (hrs) | Remarks
| Team meeting | 2019-03-30 | 1 | 1 | 1) Initial meet-up 2) Ice-breaking 3) Identification of skillsets 4) Brainstorming for project ideas
| Team meeting | 2019-05-09 | 7 | 7 | 1) Online meeting 2) Brainstorming for project ideas 3) Established rough idea of project 4) Asked friends for feedback
| Learning & Research | 2019-05-10 | 4 | 0 | 1) Research on developing Chrome extensions 2) Research on ES5 & ES6 3) Research on existing solutions
| Team meeting | 2019-05-10 | 1 | 1 | 1) Finalized full idea for project 2) Identified technologies required 3) Discussed implementation details
| Development | 2019-05-10 | 8 | 0 | 1) Looked into Panopto's implementation of webcasting page 2) Created project structure 3) Implemented CSS to resize carousel 4) Implemented mechanism to detect webpage loaded and init
| Development | 2019-05-11 | 8 | 0 | 1) Implemented sidebar 2) Implemented playback slider 3) Added CSS for LumiNUS 4) Setup code to load HTML from HTML file to separate it from code
| Development | 2019-05-12 | 8 | 0 | 1) Created class to inject JS onto webpage and retrieve data 2) Developed code to retrieve transcripts from Panopto 3) Research into VTT format, TextTracks, cues, Video element, brainstorming on subtitling implementation 4) Research into promises, closures, caniuse ES5, RS6
| Liftoff Day 1 | 2019-05-13 | 8 | 0
| Liftoff Day 2 | 2019-05-14 | 8 | 0
| Development | 2019-05-15 | 8 | 0 | 1) Setup GitHub repository for version control 2) Setup mechanic 3) Documentation 4) Reorganized some code 5) Setup readme 6) 5) Researched how to create classes in JS, created examples
| Development | 2019-05-16 | 8 | 0 | 1) Implemented processing of transcripts into subtitles 2) Implemented displaying of subtitles 3) Implemented caching of subtitles using chrome.storage.local 4) Research into JS observer pattern implementation, settled for $.Callbacks() 5) Other minor changes e.g. used CSS instead of JS to hide existing playback buttons after discovering their removal causes a race condition
| Development | 2019-05-17 | 8 | 0 | 1) Basic implementation of silence removal by detecting silent sections with Hark.js and manipulating the playback speed accordingly to fast-forward silent sections. Implementation is found to be lacking in quality. 2) Brainstorming of implementation details. 3) Research on current Panopto implementation of webcasts, research on flowplayer, HLSJS, TS, M3U8 4) Search for libraries allowing for offline processing of TS files (none found)
| Team meeting with advisor | 2019-05-18 | 1 | 0 | 1) Find out more on milestone requirements, admin stuff etc
| Development | 2019-05-20 | 7 | 0 | 1) Research on TS, fourier transform, FFT, Webassembly, Voice detection, Web Audio API, Audio Worklet, Signal Processing 2) Discovered library to play MPEG/MP2 (TS) files, started repurposing it for project 3) Setup Settings.js (for persistent settings), Video-Loaded-Event.js (logic that detects when a webcast has begun loading and callback system)
| Development | 2019-05-21 | 7 | 0 | 1) Debugging on faulty MPEG/MP2 demuxer and decoder 2) Implementation of subclasses extending from external library's implementation
| Development | 2019-05-22 | 8 | 0 | 1) Implemented MPEG/MP2 demuxer and decoder but could not decode TS files by webcast. Debugging sparks discovery that Panopto's TS audio files are not MP2 but AAC LC. 2) Search for libraries, more research on TS file format 3) Found a library on demuxing TS (supporting AAC) while implementing a demuxer for TS. Implemented demuxing and decoding of AAC files. 4) Added ES6 class examples
| Development | 2019-05-23 | 6 | 0 | 1) Worked on Milestone 1 deliverables (Document & Project log) 2) Restructuring of the Transcript class into multiple classes for SRP & OCP
| Milestone 1 Deliverables | 2019-05-24 | 6 | 0 | 1) Worked on Milestone 1 deliverables (document, video and poster)
| Team Meeting | 2019-05-31 | 6 | 6 | 1) Run through current state of project 2) Crash course into HTML/CSS & JS for Fyonn
|  | Total (hrs) | Matthew (hrs) | Fyonn (hrs)
|  | 121 | 118 | 15